## Slide 1: Update on AWCBC Prevention Committee Goal#4: Changing Workplaces: scan and the identification of gaps in prevention efforts - trends related to workers including but not limited to worker engagement, vulnerability, and equity/diversity/inclusion

## Slide 2: Updated timeline and activities
Lit scan/Proposal Development/ Work plan
Jurisdictional Scan
Report outline
Report discussion and results presentation
September 30
Complete
November 2022
Complete
Analysis of J-Scan and Subject Matter Expert Interviews
January-April
Complete
Complete
February 2023
June 2023
Not started
Report and recommendations drafted
June 2023
Not started
Preliminary report sections reviewed by PEI, Quebec
May 2023 (end)
Not started
Develop preliminary report
April-May 2023
Complete May 26

## Slide 3: Methodology for information collection

## Slide 4: Literature Scans
Google Scholar, and PubMed and websites of academic research organizations and international agencies who have published information in 2020-2022 on the topic of worker trends related to vulnerability etc. were searched:
current trends related to “workers” found in peer-reviewed literature
existing definitions of worker populations especially related to vulnerable populations
existing frameworks and programs related to the worker experience from. The methodology used in the literature search can be found in the Appendices.
Articles published by SMEs

## Slide 5: Jurisdictional scan components
Definitions of “vulnerable workers”
“Vulnerable workers” data
Funded research
Recommended SMEs
General programs and supports
Data on specific vulnerable populations
Specific programs and supports
Notes: Definitions you use of “vulnerable workers” or choose one from the literature review
How does your province identify, collect data and measure “vulnerable workers” and their risks (include results)
Any research prevention system has funded around “vulnerable workers”
Any subject matter experts within Canada, US or Europe recommend for interviews on programs/work that addresses vulnerable populations
Any programs or supports (includes short description) provided in your province that relate to “vulnerable workers” (in general)
Information on data to support that specific groups identified in literature are high risk and any programs/tools/services specifically available for identified group or sector

## Slide 6: Subject Matter Expert interviews
21 interviews completed which explored
Defining and identifying vulnerability
Research or work related to topic
Why topic of vulnerable workers is important
Common misperceptions
Biggest challenges or gaps in the system
Supports available
What needs to change
Opportunities are there for future work in research, policy, and education

## Slide 7: Preliminary Findings

## Slide 8: Key findings
A lot of the recent focus has been based on circumstance and political environment e.g. migrant workers during the pandemic, increased mental stress in first responders and healthcare, indigenous populations and related work on occupational health and safety is relatively new even though topic of “vulnerability” is not new
Using a lens of equity, diversity and inclusion in lieu of vulnerability is an emerging trend
When identifying workers at risk, prevention systems should firstly consider a focus on the situation in which the worker finds themselves and then look to secondary characteristics of the worker such as age, new to the workplace, immigrant status that may make these “vulnerable” groups even more at risk within those environments due to issues of equity, diversity and inclusion
Employers could benefit from prevention systems helping them understand why it’s important to measure and identify whether they have both OHS and EDI vulnerabilities and provide supports to reduce their health and safety risks.

## Slide 9
  Demographics
  Young workers (some older age mentions)
  Indigenous populations
  Newcomers/immigrants
  Migrant workers
  Intersectionality with age, gender, immigrant status, sectors
  Factors
  Equity
  Empowerment
  Precarious work/Three Ds
  Stigma
  Mental health
  Approaches
  Two-way communication
  Outreach
  Language and understanding
Prevalent themes from interviews

## Slide 10: Strengths
There has been attention to specific vulnerabilities in sectors/vulnerable groups. We can learn from their experience in outreach, engagement and resource development for example:
  Alberta’s Miyo pimatisiwin health and safety tool kit for indigenous employers and workers and the Manitoba Aboriginal Health and Safety Initiative (MAHSI)
  Resources for seasonal agricultural workers developed in BC and Ontario
  Immigration strategy and resources for newcomers developed in Quebec and Ontario
Concept of vulnerability has good awareness within research community and prevention systems
Availability of information:
  Lots of resources available for young and “new” workers
  There is ongoing research (e.g. IWH study) and resources available for immigrant populations in provinces
There have been efforts at translating OHS support resources – available in languages other than French and English
A measure of vulnerability (IWH OHS Vulnerability Measure) exists for employers to identify whether they have vulnerabilities in their workplace that go beyond hazard identification

## Slide 11: Challenges and Gaps – Key Issues
  Access to health and safety information/resources – while it may be available and in some cases in different languages, vulnerable groups don’t know what they don’t know and employers are not necessarily communicating either
  Even if workers know about their rights and responsibilities they are not empowered to exercise them especially if they are psychologically unsafe environments or afraid of losing their jobs
  The impact of being part of a “vulnerable” group, the stigma associated with that and not being empowered impacts mental health, and then the stigma associated with having mental health issues prevents workers from seeking help
  Challenge to help employers see that understanding and improving both OHS and strengthening EDI will benefit them (e.g.. reducing risk, improving RTW) rather than seeing it as another burden
Vulnerability is a complicated topic that impacts a broad audience and could branch out into many areas of focus

## Slide 12: Challenges and Gaps – Key Issues Cont’d
Vulnerability is a complicated topic that impacts a broad audience and could branch out into many areas of focus
  With the growing interest in EDI, is “vulnerability” a term that we should be using?
  There is a risk of focusing primarily on vulnerable groups as it highlights what may be perceived as a deficit rather than having an increased risk of injury and illness. The challenge is that the identification of inequity and inclusion may be on top of an already be a poor health and safety environment in workplaces.
  There seems to be a lack of effectiveness studies on use of support resources for groups identified as vulnerable – this is an emerging trend to look at ways of understanding and the best ways to communicate effectively with “vulnerable” groups
    E.g. language, accessibility, communication methods like videos etc., working within communities and different types of outreach

## Slide 13
One idea to consider
Threats
Acknowledgement that
  involving partners outside of prevention system e.g. immigration, may be a challenge if health and safety is not a priority item
  certain risk factors cannot be controlled e.g. prevention systems will not change:
    economic and social status of vulnerable workers
    vulnerable populations especially newcomers, migrant workers and young workers working engaging in precarious work
Cost of outreach and measurement of uptake for products developed by WCBs/AWCBC
Design supports that would help employers to improve their health and safety by identifying where they have OHS vulnerabilities using a measurement tool and how to apply a lens of equity, diversity and inclusion (ensure minority representation and understanding)
Provide practical advice on what to do if vulnerabilities exist (both OHS and EDI) including building a psychologically safe workplace

## Slide 14: Proposed next steps
Continue to develop draft report and review with PEI/Quebec
  What’s missing?
  Does it need further work?
Discuss options for finalizing report e.g. contributor recognition, sharing report beyond committee
Finalize draft report
Share draft report with interviewees for feedback
Committee to review report and provide feedback
Consider:
Whether the final report should focus on one or two key themes?
Is there an opportunity for national focus?
How can this report support each province with their current vulnerability work?

## Slide 15: Discussion